## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Beachpreneur Academy |  |  |  |  | COMPANY NAME | [8 empty] | California State University Long Beach
PROJECT MANAGER |  | Yuvika Nibber |  |  |  |  | DATE | [8 empty] | 2022-01-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR | [15 empty] | PHASE FIVE
[7 empty] | WEEK 1 (1/10-1/17) | [6 empty] | WEEK 2 (1/18-1/25) | [8 empty] | WEEK 3 (1/26-2/2) |  |  |  |  | WEEK 4 (2/3-2/10) | [6 empty] | WEEK 5 (2/11-2/18) | [6 empty] | WEEK 6 (2/19-2/26) | [6 empty] | WEEK 7 (2/27-3/6) | [6 empty] | WEEK 8 (3/7-3/14) | [6 empty] | WEEK 9 (3/15-3/22) | [6 empty] | WEEK 10 (3/23-3/30) | [6 empty] | WEEK 11 (3/31-4/7) |  |  |  |  | WEEK 12 (4/8-4/15) |  |  | WEEK 13 (4/16-4/23) | WEEK 14 (4/24-5/1) | WEEK 15 (5/2-5/9) | WEEK 16 (5/10-5/17)
[7 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | First Implementation
1.1 | Drink Selection/Information UI | Nicholas Bautista | 2021-10-04 | 2021-10-05 | 1 | 100% | bar: WEEK 1 (1/10-1/17) M; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
1.2 | Drink Page Template UI | Matt Ortiz | 2021-10-04 | 2021-10-05 | 1 | 100% | bar: WEEK 1 (1/10-1/17) M; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
1.3 | Home Page Format/Information | Andrew Baltazar | 2021-10-04 | 2021-10-06 | 2 | 100% | bar: WEEK 1 (1/10-1/17) M to WEEK 1 (1/10-1/17) T; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
1.4 | Shop Page UI | Nicholas Bautista | 2021-10-04 | 2021-10-07 | 3 | 100% | bar: WEEK 1 (1/10-1/17) M to WEEK 1 (1/10-1/17) W; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
1.5 | Style/Icon/Image Implementation | Yuvika Nibber | 2021-10-04 | 2021-10-04 | 1 | 100% | bar: WEEK 1 (1/10-1/17) M; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
2 | Database
2.1 | Plan and document database | All | 2021-10-11 | 2021-10-15 | 5 | 100% | bar: WEEK 2 (1/18-1/25) M to WEEK 2 (1/18-1/25) F; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
2.2 | Add Company Info to Database | Andrew Baltazar | 2021-10-16 | 2021-10-17 | 2 | 100% | bar: WEEK 2 (1/18-1/25) S to WEEK 2 (1/18-1/25) U; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
2.3 | Display Available Merch | Nicholas Bautista | 2021-10-18 | 2021-10-23 | 6 | 100% | bar: WEEK 2 (1/18-1/25) M to WEEK 3 (1/26-2/2) S; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
2.4 | Record schedule info | Yuvika Nibber | 2021-10-20 | 2021-10-23 | 4 | 100% | bar: WEEK 3 (1/26-2/2) W to WEEK 3 (1/26-2/2) S; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
2.5 | Document and record merchandise info | Matt Ortiz | 2021-10-22 | 2021-10-23 | 2 | 100% | bar: WEEK 3 (1/26-2/2) F to WEEK 3 (1/26-2/2) S; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
3 | Mobile Order Functionality
3.1 | Connect database to its own page | All | 2021-10-24 | 2021-10-30 | 7 | 100% | bar: WEEK 3 (1/26-2/2) U to WEEK 4 (2/3-2/10) R; WEEK 5 (2/11-2/18) U; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
3.2 | Update the database stock info | All | 2021-10-28 | 2021-11-02 | 6 | 100% | bar: WEEK 4 (2/3-2/10) R to WEEK 5 (2/11-2/18) T; WEEK 5 (2/11-2/18) U; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
3.2.1 | Set up venmo payment system | Yuvika/Nicholas | 2021-10-24 | 2021-11-06 | 5 | 100% | bar: WEEK 5 (2/11-2/18) T to WEEK 5 (2/11-2/18) U; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
3.2.2 | Email receipt / test cases | Andrew Baltazar | 2021-10-24 | 2021-11-07 | 2 | 100% | bar: WEEK 5 (2/11-2/18) F to WEEK 5 (2/11-2/18) U; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
3.3 | Email order / test cases | Matt Ortiz | 2021-10-24 | 2021-11-06 | 2 | 100% | bar: WEEK 5 (2/11-2/18) F to WEEK 5 (2/11-2/18) U; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
3.3.1 | Store order information in database | All | 2021-10-24 | 2021-11-06 | 1 | 100% | bar: WEEK 5 (2/11-2/18) S to WEEK 5 (2/11-2/18) U; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4 | Drink Template UI
4.1 | Stored procedure planning | All | 2021-11-07 | 2021-11-10 | 4 | 100% | bar: WEEK 5 (2/11-2/18) M to WEEK 5 (2/11-2/18) T; WEEK 5 (2/11-2/18) U to WEEK 6 (2/19-2/26) W; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.2 | Email integration | Matt Ortiz | 2021-11-03 | 2021-11-12 | 4 | 100% | bar: WEEK 5 (2/11-2/18) M to WEEK 5 (2/11-2/18) T; WEEK 6 (2/19-2/26) T to WEEK 6 (2/19-2/26) F; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.3 | Count frequency of orders | Yuvika Nibber | 2021-11-07 | 2021-11-13 | 7 | 100% | bar: WEEK 5 (2/11-2/18) M to WEEK 5 (2/11-2/18) T; WEEK 5 (2/11-2/18) U to WEEK 6 (2/19-2/26) S; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.4 | Verify data is correct with customer | Nicholas Bautista | 2021-11-13 | 2021-11-13 | 1 | 100% | bar: WEEK 5 (2/11-2/18) M to WEEK 5 (2/11-2/18) T; WEEK 6 (2/19-2/26) S; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
5 | Schedule display
4.1 | Create page for schedule | Nicholas Bautista | 2021-11-14 | 2021-11-15 | 4 | 100% | bar: WEEK 6 (2/19-2/26) U to WEEK 7 (2/27-3/6) W; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.2 | Connect to google map api | Matt Ortiz | 2021-11-15 | 2021-11-17 | 3 | 100% | bar: WEEK 7 (2/27-3/6) M to WEEK 7 (2/27-3/6) W; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.3 | Display schedule | Yuvika Nibber | 2021-11-15 | 2021-11-18 | 4 | 100% | bar: WEEK 7 (2/27-3/6) M to WEEK 7 (2/27-3/6) R; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.4 | Integrate mapped area | All | 2021-11-17 | 2021-11-18 | 2 | 100% | bar: WEEK 7 (2/27-3/6) W to WEEK 7 (2/27-3/6) R; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.5 | Develop Test cases for integration | Andrew Baltazar | 2021-11-14 | 2021-11-17 | 4 | 100% | bar: WEEK 6 (2/19-2/26) U to WEEK 7 (2/27-3/6) W; WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
6 | Social media implementation
4.1 | Links to Yelp/ instagram at bottom | All | 2021-11-19 | 2021-11-20 | 2 | 100% | bar: WEEK 7 (2/27-3/6) F to WEEK 7 (2/27-3/6) S; WEEK 8 (3/7-3/14) R
4.2 | Contact us form | Matt Ortiz | 2021-11-19 | 2021-11-23 | 4 | 100% | bar: WEEK 7 (2/27-3/6) S to WEEK 8 (3/7-3/14) R
4.3 | Store contact info in database | Yuvika Nibber | 2021-11-21 | 2021-11-22 | 2 | 100% | bar: WEEK 7 (2/27-3/6) U to WEEK 8 (3/7-3/14) M
4.4 | Display most recent post from instagram | Andrew Baltazar | 2021-11-22 | 2021-11-23 | 5 | 100% | bar: WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) R
4.5 | GIF/icon implementation | Nicholas Bautista | 2021-11-22 | 2021-11-24 | 3 | 100% | bar: WEEK 8 (3/7-3/14) M to WEEK 8 (3/7-3/14) W
7 | Newsletter/feedback forms
4.1 | Table to house user data in db | All | 2021-11-27 | 2021-11-28 | 2 | 100% | bar: WEEK 8 (3/7-3/14) M; WEEK 8 (3/7-3/14) S to WEEK 8 (3/7-3/14) U
4.2 | Draft template feedback form | Matt Ortiz | 2021-11-29 | 2021-12-01 | 1 | 100% | bar: WEEK 8 (3/7-3/14) M; WEEK 9 (3/15-3/22) M to WEEK 9 (3/15-3/22) W
4.3 | Draft newsletter template | Yuvika Nibber | 2021-11-30 | 2021-12-03 | 1 | 100% | bar: WEEK 8 (3/7-3/14) M; WEEK 9 (3/15-3/22) T to WEEK 9 (3/15-3/22) F